## Scrum - EnergyMatrix
EnergyMatrix
Resource | Menu | Screens / Functionalities | API | React Integration | Target date | Days | Unit Test | UAT Release
Bhava | Masters | Customers | Dev Completed | Completed |  | 4
|  | Windmill | Dev Completed | Completed |  | 3
|  | EDC | Dev Completed | Completed |  | 1
|  | Investors | Dev Completed | Completed |  | 1
|  | Log maintenance for all Masters |  |  |  | 2
| Transactions | Client EB Bill | Dev Completed | In Progress
|  | Allotment | Yet To Start | Yet To Start
|  | EB Statement Solar | Dev Completed | Yet To Start
Log maintenance for all Transactions
Kabilesh | Masters | Email | Dev Completed | Completed |  | 4
|  | Transmission Loss | Dev Completed | In Progress
|  | Share Holding | Dev Completed | Completed
|  | Consumption charges | Dev Completed | Yet to Start
Log maintenance for all Masters
| Transactions | Daily Transactions | Dev Completed | Completed
Log maintenance for all Transactions
Melvin | Transactions | Cust Consumption Request | Dev Completed | Completed
|  | EB Statement | Dev Completed | Completed
Sachin | Dev Ops | DB set up | In Progress
|  | Build files set up | Yet to Start
|  | Final URL | Yet to Start
|  | Log check for Masters | Yet to Start
|  | Log check for Transactions | Yet to Start
Final check | Code review

## Code Review - Code review param
Code review parameters
No Inline Queries | Stored procedure is must
No direct parameters | Need to use variables with proper name
Error handling | Must use Try… Catch for all functionalities
Functions | No functions code more than 100 lines
Hardcode data | No hardcode data in any of the functions
Configurations | In all configuration files (like mail config, app config) comment needed for the added values
Code page | Any important validation / change needs to be with a proper comment
Logs | Logs should be maintained for Masters and Transactions
Login Logs | Who logged in, which time, when logged out; must be in the Login Log table